## Sheet1
Conestoga College
Team: | Grey Cube Development
Jeff Pritchard, Mitchell Duggan, Russell Tremain, Kevin Wang
Agile Product Feature List - Backlog Template
# | Description | hours est. | Resources
High Priority
Iteration 1
1 | View games | 7 | JP, MD, RT, KW
2 | Add game | 7 | JP, MD, RT, KW
4 | Delete Game | 7 | JP, MD, RT, KW
5 | View events | 7 | JP, MD, RT, KW
6 | Add event | 7 | JP, MD, RT, KW
8 | Delete event | 7 | JP, MD, RT, KW
9 | View reports | 4 | JP, MD, RT, KW
15 | Log In | 6 | JP, MD, RT, KW
Iteration 2
14 | Visitor registers | 6 | JP, MD, RT, KW
16 | View profile | 5 | JP, MD, RT, KW
19 | Edit profile | 6 | JP, MD, RT, KW
24 | Search games | 4 | JP, MD, RT, KW
25 | View game details | 3 | JP, MD, RT, KW
34 | Add to cart | 4 | JP, MD, RT, KW
35 | Delete from cart | 4 | JP, MD, RT, KW
36 | Check out | 4 | JP, MD, RT, KW
37 | Submit order | 4 | JP, MD, RT, KW
40 | Log out | 4 | JP, MD, RT, KW
45 | View cart | 4 | JP, MD, RT, KW
46 | Edit cart | 5 | JP, MD, RT, KW
Iteration 3
22 | Add credit card | 4 | JP, MD, RT, KW
28 | View friends | 4 | JP, MD, RT, KW
29 | Add friend | 4 | JP, MD, RT, KW
30 | Delete friend | 3 | JP, MD, RT, KW
38 | Download game | 4 | JP, MD, RT, KW
43 | View pending shipments | 3 | JP, MD, RT, KW
Medium Priority
Iteration 1
3 | Edit game | 5 | JP, MD, RT, KW
7 | Edit event | 5 | JP, MD, RT, KW
10 | View a report | 6 | JP, MD, RT, KW
Iteration 2
17 | Reset password | 5 | JP, MD, RT, KW
20 | Edit mailing address | 4 | JP, MD, RT, KW
21 | Edit shipping address | 4 | JP, MD, RT, KW
Iteration 3
11 | Publish review | 4 | JP, MD, RT, KW
13 | Update status of ship | 4 | JP, MD, RT, KW
23 | Delete credit card | 3 | JP, MD, RT, KW
26 | Add to wish list | 4 | JP, MD, RT, KW
27 | Remove game from wish list | 4 | JP, MD, RT, KW
32 | Rate game | 4 | JP, MD, RT, KW
33 | Add game review | 5 | JP, MD, RT, KW
39 | Register for event | 4 | JP, MD, RT, KW
41 | View pending reviews | 3 | JP, MD, RT, KW
42 | Reject review | 3 | JP, MD, RT, KW
44 | View own wishlist | 3 | JP, MD, RT, KW
Low Priority
Iteration 1
18 | Change Password | 5 | JP, MD, RT, KW
Iteration 2
Iteration 3
31 | View friend's wish list | 4 | JP, MD, RT, KW