## Sheet1
Conestoga College
Team: | Grey Cube Development
Jeff Pritchard, Mitchell Duggan, Russell Tremain, Kevin Wang
Agile Product Feature List - Backlog Template
# | Description | hours est. | By
High Priority
Iteration 1
1 | View games | 7 | JP, MD, RT, KW
2 | Add game | 7 | JP, MD, RT, KW
4 | Delete Game | 7 | JP, MD, RT, KW
5 | View events | 7 | JP, MD, RT, KW
6 | Add event | 7 | JP, MD, RT, KW
8 | Delete event | 7 | JP, MD, RT, KW
9 | View reports | 4 | JP, MD, RT, KW
15 | Log In | 6 | JP, MD, RT, KW
Iteration 2
Iteration 3
Medium Priority
Iteration 1
3 | Edit game | 5 | JP, MD, RT, KW
7 | Edit event | 5 | JP, MD, RT, KW
10 | View a report | 6 | JP, MD, RT, KW
Low Priority
Iteration 1
18 | Change Password | 5 | JP, MD, RT, KW
wishlist / friends