## Sheet1
GREY CUBE DEVELOPMENT
Team: | Mitchell Duggan, Jeff Pritchard, Russell Tremain, Kevin (Qiao) Wang
Release Plan Summary
|  | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: Sept 21 | Due: Oct 12, 2018 | Due: Nov 9, 2018 | Due: Nov 30, 2018 | Due: Dec 7, 2018
# | Feature / Requirement
1 | Project Vision statement | 4
…
110 | Modify the calculation of orders total |  | 1
101 | Add a new Invoice |  | 4
…
107 | Need ability to capture customer contact |  |  | 2
109 | Create report of invoices generated daily |  |  | 2
…
…
| Work Effort in Person Days (PD) | 4 | 5 | 4 | 0 | 0 | 13 | Target: 135 to 150 PD for team of 3
Given: 1 PD = 4 hours
Estimate: 3 PD per week = 45 PD per member; 135 PD for team of 3