## Sheet1
GREY CUBE DEVELOPMENT
Team: | Mitchell Duggan, Jeff Pritchard, Russell Tremain, Kevin (Qiao) Wang
Release Plan Summary
|  | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: Sept 21 | Due: Oct 12, 2018 | Due: Nov 9, 2018 | Due: Nov 30, 2018 | Due: Dec 7, 2018
# | Feature / Requirement
1 | Team Charter | 4
2 | Project Charter | 6
3 | Project Plan | 4
4 | Use Case Diagrams |  | 4
5 | Use Case Descriptions with Activity Diagrams |  | 6
6 | Analysis Level Class Diagram |  | 1.5
7 | System Sequence Diagrams |  | 2
8 | Design Level Class Diagram |  | 3
9 | Design Level Sequence Diagrams |  | 4
10 | Navigation Diagrams |  | 2
11 | User Interface Prototype |  | 4
12 | Report Designs |  | 2.5
13 | Entity Relationship Diagram |  | 2
14 | Data Dictionary |  | 2
15 | Unit Test Plan* (not required) |  | 0
16 | Source Code |  | 20
17 | Agile Backlog Report |  | 3
18 | Agile Summary Report |  | 2
19 | Use Case Diagrams | [5 empty] | X
20 | Use Case Descriptions with Activity Diagrams | [5 empty] | 50%
21 | Analysis Level Class Diagram | [5 empty] | X
22 | System Sequence Diagrams | [5 empty] | X
23 | Design Level Class Diagram | [5 empty] | X
24 | Design Level Sequence Diagrams | [5 empty] | X
25 | Navigation Diagrams | [5 empty] | 0%
26 | User Interface Prototype | [5 empty] | 0%
27 | Report Designs | [5 empty] | X
28 | Entity Relationship Diagram | [5 empty] | X
29 | Data Dictionary |  |  | 1.5 |  |  | X
30 | Unit Test Plan* (not required) |  |  | 5 |  |  | X
31 | Source Code | [5 empty] | X
32 | Agile Backlog Report | [5 empty] | X
33 | Agile Summary Report | [5 empty] | 50%
…
| Work Effort in Hours | 14 | 58 | 6.5 | 0 | 0 | 78.5