## Sheet1
GREY CUBE DEVELOPMENT
Team: | Mitchell Duggan, Jeff Pritchard, Russell Tremain, Kevin (Qiao) Wang
Release Plan Summary
|  | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: Sept 21 | Due: Oct 12, 2018 | Due: Nov 9, 2018 | Due: Nov 30, 2018 | Due: Dec 7, 2018
# | Feature / Requirement
1 | Team Charter | 4
2 | Project Charter | 6
3 | Project Plan | 4
4 | Use Case Diagrams |  | 4
5 | Use Case Descriptions with Activity Diagrams |  | 6
6 | Analysis Level Class Diagram |  | 1.5
7 | System Sequence Diagrams |  | 2
8 | Design Level Class Diagram |  | 3
9 | Design Level Sequence Diagrams |  | 4
10 | Navigation Diagrams |  | 2
11 | User Interface Prototype |  | 4
12 | Report Designs |  | 2.5
13 | Entity Relationship Diagram |  | 2
14 | Data Dictionary |  | 2
15 | Unit Test Plan* (not required) |  | 0
16 | Source Code |  | 20
17 | Agile Backlog Report |  | 3
18 | Agile Summary Report |  | 2
19 | Use Case Diagrams |  |  | 4
20 | Use Case Descriptions with Activity Diagrams |  |  | 6
21 | Analysis Level Class Diagram |  |  | 1.5
22 | System Sequence Diagrams |  |  | 2.5
23 | Design Level Class Diagram |  |  | 2
24 | Design Level Sequence Diagrams |  |  | 2
25 | Navigation Diagrams |  |  | 2
26 | User Interface Prototype |  |  | 4
27 | Report Designs |  |  | 3
28 | Entity Relationship Diagram |  |  | 2
29 | Data Dictionary |  |  | 2
30 | Unit Test Plan* (not required) |  |  | 5
31 | Source Code |  |  | 32
32 | Agile Backlog Report |  |  | 2
33 | Agile Summary Report |  |  | 3
| Use Case Diagrams |  |  |  | 4
| Use Case Descriptions with Activity Diagrams |  |  |  | 6
| Analysis Level Class Diagram |  |  |  | 1.5
| System Sequence Diagrams |  |  |  | 2.5
| Design Level Class Diagram |  |  |  | 2
| Design Level Sequence Diagrams |  |  |  | 2
| Navigation Diagrams |  |  |  | 2
| User Interface Prototype |  |  |  | 4
| Report Designs |  |  |  | 3
| Entity Relationship Diagram |  |  |  | 2
| Data Dictionary |  |  |  | 2
| Unit Test Plan* (not required) |  |  |  | 5
| Source Code |  |  |  | 32
| Agile Backlog Report |  |  |  | 2
| Agile Summary Report |  |  |  | 3
| Work Effort in Hours | 14 | 58 | 73 | 73 | 0 | 218